## Sheet1
Task | APR |  |  |  | MAY |  |  |  | JUN |  |  |  | JUL |  |  |  | AUG |  |  |  | SEP
| w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4
PHASE 1 - PLANNING & REQUIREMENTS
Team Setup | bar: APR w1
Requirement Gathering | bar: APR w1 to APR w2
Project Proposal | bar: APR w2 to APR w3
Project Charter | bar: APR w2 to APR w4
Risk documentation | bar: APR w4
Milestone Approved | APR w4: TRUE
PHASE 2 - SYSTEM DESIGN
System Architecture Design | bar: MAY w1 to MAY w2
Database Schema Design | bar: MAY w1 to MAY w3
UI/UX wirefram | bar: MAY w2 to MAY w4
Interactive Prototype | bar: MAY w3 to JUN w1
Milestone Approved | JUN w1: TRUE
PHASE 3 - DEVELOPMENT
FrontEnd Dev (React.js) | bar: JUN w2 to JUL w4
Backend Dev (Supabase / PostgresSQL) | bar: JUN w2 to JUL w4
Database Implematention (SQL) | bar: JUN w2 to JUL w1
Security Implementation (RLS / Policies) | bar: JUL w2 to JUL w4
Integration Testing | JUL w4: TRUE
PHASE 4 - IMPLEMENTATION & DEV
System Deployment | bar: AUG w3 to AUG w4
test and fix bugs | AUG w4: TRUE
PHASE 5 — USER ACCEPTANCE TESTING
UAT with 30 Users | bar: AUG w4 to SEP w1
Feedback Analysis & Fixes | bar: AUG w4 to SEP w1
Milestone Approved | SEP w1: TRUE
PHASE 6 - DOCUMENTATION
Final Documentation | bar: SEP w2 to SEP w3
Final Report & Submission | bar: SEP w4
SUBMISSION | SEP w4: TRUE